## CLERK
Action | Comments | Officer | RAG | Raking | Target Date
look into legal advice to lease the wildlife reserve and playspace to charity | send copy of lease to legal reps | Clerk
research more equipment for playground | In progress | Clerk
email mike about funding for playspace, email jo about benches | cant be done until we know whats happening with playspace | Clerk
Email sutton and rcce for meeting date | sent awaiting reply | Clerk
Get quotes for reseurface of car park | make another report with further qoutes for option 1 | Clerk
get quotes for cctv at the wlr | awaiting replies | Clerk
chase up with kim about use of parry | done reply received | Clerk
send over tree survey reports once received | report received added to agenda | Clerk
Order bins for playspace, parry and mucking hall road | awaiting unity bank card | Clerk
write to farmers about placing signs for dog waste on their lands | received rply from tabor farms. Will follow up with mike after elections | Clerk
Speak to rdc about parry use and adding dog waste bins to areas in barling | received reply | Clerk
arrange a sheet for first aid boxes | waiting to order accident books | Clerk
email essex steel for prices | done | Clerk
investigate cracked glass above fire exit door | quotes received added to agenda | Clerk
investigate fire door peeling | received added to agenda | Clerk
add standing items on agenda | done | Clerk
set date with emma for committee room papers | in progress | Clerk
sort steves contract | done | Clerk
email sally about nationwide bank | reply received | Clerk
send out light spreadsheet again to cllrs | added to agenda paperwork | Clerk
arrange new committees | done | Clerk
email working party regarding the assett register | setting date at meeting | Clerk
sort risk assessments | basic risk assessment done | Clerk
investigate new community events | in progress | Clerk
make list of key holders and receive keys to make master keys | awaiting replies | Clerk
set date for personnell committee meeting for upcoming pay rises | added to agenda | Clerk
set date for apprasials | in progress | Clerk
Advertise community events on socials | Will start early may | Clerk
Sort one drive | In Progress | Clerk
Daily/Weekly
Check emails, deal with or answer |  | Clerk/ RFO
Website and Facebook update |  | Clerk/ RFO
Street Light Reports |  | Clerk
Staff support and training |  | RFO
Monthly
Monthly wages |  | RFO
· Basic Tools
· Bank
· Scribe
· Payment list
· Submit to HMRC
Prepare the monthly payment list |  | RFO
Meetings |  | Clerk/ RFO
at least monthly some months more than one meeting
Prepare agenda | 8 Working days before meeting (Monday)
Draft Agenda to Chair & Vice | 8 Working days before meeting (Monday)
Response from Chair & Vice Chair | 6 Working days before meeting (Wednesday)
Issue Papers to councillors | Friday before Meeting
Put Agenda on noticeboards | Friday before Meeting
Put agenda on website & Facebook | Friday before Meeting
Attend Meeting
Write Minutes | Within 5 working days after meeting
Draft Minutes to Chair & Vice | Within 7 working days after meeting
Put on website | Within 10 working days after meeting
Put signed minutes on website | Within 10 working days after meeting | Clerk

## WEBSITE
Action | Comments | Officer | RAG | Raking | Target Date
add wording to minutes page | in progress | Clerk
from september 2025 on add minutes | in progress | Clerk
add pictures to local events page | in progress | Clerk
sort policies page and add new policies to page | in progress | Clerk
find 2023 monthly payments | in progress | Clerk
add 5 years of budget and precept | in progress | Clerk
add audit reports | in progress | Clerk
add more photos to gallery | in progress | Clerk
change sally to emma in contact page | in progress | Clerk
add register of interest to contacts page | in progress | Clerk