## CLERK
Action | Comments | Officer | RAG | Raking | Target Date
look into legal advice to lease the wildlife reserve and playspace to charity | send copy of lease to legal reps | Clerk
research more equipment for playground to include disabled play equipment | In progress | Clerk
email mike about funding for playspace, email jo about benches | cant be done until we know whats happening with playspace | Clerk
Email sutton and rcce for meeting date | awaiting dates from barry | Clerk
Get quotes for reseurface of car park | make another report with further qoutes for option 1 | Clerk
get quotes for cctv at the wlr | awaiting last quotes | Clerk
Order bins for playspace, parry and mucking hall road | awaiting unity bank card | Clerk
arrange a sheet for first aid boxes | waiting to order accident books | Clerk
set date with emma for committee room papers | In progress | Clerk
email working party regarding the assett register | meeting set 15th june | Clerk
sort risk assessments | cant do until asset register complete | Clerk
make list of key holders and receive keys to make master keys | done | Clerk
Upload new policies to the website | done | Clerk
write a letter to warren lamb | done | Clerk
Contact neighbour next to tree to inform them of noise when tree taken away | letter written awaiting dates of removal and quote to remove. | Clerk
Send out meeting dates | Done | Clerk
Email richard about fire door | Done | Clerk
Fill out CGR with mike for Council | Done | Clerk
Get quotes for painting at hall | awaiting last quote | Clerk
Send spreadsheet to Cllrs | Done | Clerk
Contact Mandy about land registry | to contact in a few weeks | Clerk
Contact pss and pay in full | done | Clerk
Write to land owner at the parry about boundry issue | jo to write ot them report written for Council | Clerk
Email steve about contarct | Done | Clerk
Pay insurance renewal | done | Clerk
investigate new community events | In progress | Clerk
set date for apprasials | in progress | Clerk
Advertise community events on socials | in progress | Clerk
Sort one drive | In Progress | Clerk
Daily/Weekly
Check emails, deal with or answer |  | Clerk/ RFO
Website and Facebook update |  | Clerk/ RFO
Street Light Reports |  | Clerk
Staff support and training |  | RFO
Monthly
Monthly wages |  | RFO
· Basic Tools
· Bank
· Scribe
· Payment list
· Submit to HMRC
Prepare the monthly payment list |  | RFO
Meetings |  | Clerk/ RFO
at least monthly some months more than one meeting
Prepare agenda | 8 Working days before meeting (Monday)
Draft Agenda to Chair & Vice | 8 Working days before meeting (Monday)
Response from Chair & Vice Chair | 6 Working days before meeting (Wednesday)
Issue Papers to councillors | Friday before Meeting
Put Agenda on noticeboards | Friday before Meeting
Put agenda on website & Facebook | Friday before Meeting
Attend Meeting
Write Minutes | Within 5 working days after meeting
Draft Minutes to Chair & Vice | Within 7 working days after meeting
Put on website | Within 10 working days after meeting
Put signed minutes on website | Within 10 working days after meeting | Clerk

## WEBSITE
Action | Comments | Officer | RAG | Raking | Target Date
add wording to minutes page | in progress | Clerk
from september 2025 on add minutes | in progress | Clerk
add pictures to local events page | in progress | Clerk
sort policies page and add new policies to page | in progress | Clerk
find 2023 monthly payments | in progress | Clerk
add 5 years of budget and precept | in progress | Clerk
add audit reports | in progress | Clerk
add more photos to gallery | in progress | Clerk
change sally to emma in contact page | in progress | Clerk
add register of interest to contacts page | in progress | Clerk