## CLERK
Action | Comments | Officer | RAG
look into legal advice to lease the wildlife reserve and playspace to charity | find play space lease and wildlife lease and send | Clerk
research more equipment for playground to include disabled play equipment | In progress | Clerk
email mike about funding for playspace, email jo about benches | cant be done until we know whats happening with playspace | Clerk
Email sutton and rcce for meeting date | awaiting replies on emails | Clerk
Get quotes for reseurface of car park | report written awaiting more quotes | Clerk
email cview regarding quote | date set peter avilable | Clerk
Order bins for playspace, parry and mucking hall road | awaiting unity bank card | Clerk
email steve about cutting of bushes near salt bin and waste bin at the church | done | Clerk
set date with emma for committee room papers | In progress | Clerk
get noticeboard key cut for window cleaner | Done | Clerk
cancel ee phone and email andrew about getting new phone | done | Clerk
create poster for october quiz ask mandy if she would like to help again | awaiting replies from fish shops | Clerk
email barling school regarding entries for photgraphy comp | email sent 13/07/2026 | Clerk
order new sign for the village hall | awaiting charge card | Clerk
Contact neighbour next to tree to inform them of noise when tree taken away | letter written awaiting dates of removal and quote to remove. | Clerk
order new flag for village hall | awaiting charge card | Clerk
double check gdpr training | ask council if they still want me to go ahead with this | Clerk
contact tree companies about cutting of tree at VH | Steve Done | Clerk
Contact Steve about issues at the VH | Steve booked in | Clerk
chase painter for start date | date set | Clerk
Apply for funding for bike rack | Done | Clerk
set up working group for play equipment | done | Clerk
Check light in gents toilet | in progress | Clerk
Contact Mandy about land registry | emailed 13/07/2026 | Clerk
quotes for varnish of sign post | in progress | Clerk
set up working group for emergency plan | on agenda to do | Clerk
Write to land owner at the parry about boundry issue | done. Need to send | Clerk
investigate new community events | In progress | Clerk
set date for apprasials | in progress | Clerk
Advertise community events on socials | in progress | Clerk
Sort one drive | In Progress | Clerk
Daily/Weekly
Check emails, deal with or answer |  | Clerk/ RFO
Website and Facebook update |  | Clerk/ RFO
Street Light Reports |  | Clerk
Staff support and training |  | RFO
Monthly
Monthly wages |  | RFO
· Basic Tools
· Bank
· Scribe
· Payment list
· Submit to HMRC
Prepare the monthly payment list |  | RFO
Meetings |  | Clerk/ RFO
at least monthly some months more than one meeting
Prepare agenda | 8 Working days before meeting (Monday)
Draft Agenda to Chair & Vice | 8 Working days before meeting (Monday)
Response from Chair & Vice Chair | 6 Working days before meeting (Wednesday)
Issue Papers to councillors | Friday before Meeting
Put Agenda on noticeboards | Friday before Meeting
Put agenda on website & Facebook | Friday before Meeting
Attend Meeting
Write Minutes | Within 5 working days after meeting
Draft Minutes to Chair & Vice | Within 7 working days after meeting
Put on website | Within 10 working days after meeting
Put signed minutes on website | Within 10 working days after meeting | Clerk

## WEBSITE
Action | Comments | Officer | RAG | Raking | Target Date
add wording to minutes page | in progress | Clerk
from september 2025 on add minutes | in progress | Clerk
add pictures to local events page | in progress | Clerk
sort policies page and add new policies to page | in progress | Clerk
find 2023 monthly payments | in progress | Clerk
add 5 years of budget and precept | in progress | Clerk
add audit reports | in progress | Clerk
add more photos to gallery | in progress | Clerk
change sally to emma in contact page | in progress | Clerk
add register of interest to contacts page | in progress | Clerk