## CLERK
Action | Comments | Officer | RAG | Target Date
look into legal advice to lease the wildlife reserve and playspace to charity | still need to find the playspace lease. | Clerk |  | 2026-09-10
research more equipment for playgrounds to include disabled play equipment | awaiting date for meeting. | Clerk |  | 2026-10-08
email mike about funding for playspace, email jo about benches | cant be done until we know whats happening with playspace | Clerk |  | 2026-09-10
Email sutton and rcce for meeting date | Date set 14th september 2026 emailed gilly | Clerk |  | 2026-09-14
Get quotes for reseurface of car park | report written awaiting more quotes | Clerk |  | 2026-09-10
email cview about adding remote access | emailed today 14/08/2026 | Clerk |  | 2026-09-10
Order bins for playspace, parry and mucking hall road | awaiting unity bank card 4- 6 weeks | Clerk |  | 2026-09-25
Email tree vedors for dates of tree removals | awaiting dates to be set | Clerk |  | 2026-09-10
set date with emma for committee room papers | In progress | Clerk |  | 2026-10-08
get details for donation for essex ambulance | details received sent to emma on 28/08/2026 | Clerk |  | 2026-08-17
write thank you letter to window cleaner | done | Clerk |  | 2026-08-17
create poster get it sent out | poster circulated | Clerk |  | 2026-09-10
email anne about light out | done | Clerk |  | 2026-08-17
order new sign for the village hall | awaiting charge card | Clerk |  | 2026-09-25
Contact neighbour next to tree to inform them of noise when tree taken away | sending out next week after date received | Clerk |  | 2026-08-17
order new flag for village hall | awaiting charge card | Clerk |  | 2026-09-25
add barling heritage website, benches at playspace, singer for cameo and keep fit event to next agenda | done | Clerk |  | 2026-09-10
contact steve and agree to quote get address changed and advise of not cutting till next month | Done. | Clerk |  | 2026-09-17
create helath and safety and ai policy add to next agenda | Done | Clerk |  | 2026-09-10
check prices for cllr emails | in progess | Clerk |  | 2026-09-10
order testing kits for water | awaiting charge card | Clerk |  | 2026-09-10
set date for working group for ememergency plan | emailed awaiting reply | Clerk |  | 2026-10-08
Check light in gents toilet | in progress | Clerk |  | 2026-09-10
fill out land registry forms | in progress | Clerk |  | 2026-09-17
quotes for varnish of sign post | emailed richard awaiting reply | Clerk |  | 2026-09-10
email ealc regarding creating a delegated committee | done need a council resolution | Clerk |  | 2026-10-08
Rewrite letter to parry boundry resident | approval done letter sent. | Clerk |  | 2026-09-17
email romac re the pole | done awaiting date to be set | Clerk |  | 2026-09-17
create spreadsheet and report for cio email emma about what needs to be included | In progress | Clerk |  | 2026-10-08
set date for apprasials | in progress | Clerk |  | 2026-10-08
Daily/Weekly
Check emails, deal with or answer |  | Clerk/ RFO
Website and Facebook update |  | Clerk/ RFO
Street Light Reports |  | Clerk
Staff support and training |  | RFO
Monthly
Monthly wages |  | RFO
· Basic Tools
· Bank
· Scribe
· Payment list
· Submit to HMRC
Prepare the monthly payment list |  | RFO
Meetings |  | Clerk/ RFO
at least monthly some months more than one meeting
Prepare agenda | 8 Working days before meeting (Monday)
Draft Agenda to Chair & Vice | 8 Working days before meeting (Monday)
Response from Chair & Vice Chair | 6 Working days before meeting (Wednesday)
Issue Papers to councillors | Friday before Meeting
Put Agenda on noticeboards | Friday before Meeting
Put agenda on website & Facebook | Friday before Meeting
Attend Meeting
Write Minutes | Within 5 working days after meeting
Draft Minutes to Chair & Vice | Within 7 working days after meeting
Put on website | Within 10 working days after meeting
Put signed minutes on website | Within 10 working days after meeting | Clerk

## WEBSITE
Action | Comments | Officer | RAG | Raking | Target Date
add wording to minutes page | in progress | Clerk
from september 2025 on add minutes | in progress | Clerk
add pictures to local events page | in progress | Clerk
sort policies page and add new policies to page | in progress | Clerk
find 2023 monthly payments | in progress | Clerk
add 5 years of budget and precept | in progress | Clerk
add audit reports | in progress | Clerk
add more photos to gallery | in progress | Clerk
change sally to emma in contact page | in progress | Clerk
add register of interest to contacts page | in progress | Clerk