## CLERK
Action | Comments | Officer | RAG | Target Date
look into legal advice to lease the wildlife reserve and playspace to charity | still need to find the playspace lease. | Clerk |  | 2026-12-01
research more equipment for playgrounds to include disabled play equipment | date set 5th october | Clerk |  | 2026-10-05
email mike about funding for playspace, email jo about benches | to be brought up at playspace working group meeting | Clerk |  | 2026-10-05
Email sutton and rcce for meeting date | done | Clerk |  | 2026-09-14
Get quotes for reseurface of car park | report written awaiting more quotes | Clerk |  | 2026-10-08
email cview about adding remote access | done | Clerk |  | 2026-09-10
Order bins for playspace, parry, mucking hall road and stonebridge | looking into supports for bins | Clerk |  | 2026-10-01 | 4 dog waste and 1 general waste
Email tree vedors for dates of tree removals | one date set for the 14th October 2026 at 8:30 am send letter to neighbours | Clerk |  | 2026-10-01 | email tabor
set date with emma for committee room papers | done | Clerk |  | 2026-10-08 | clearance man
barling heritage website investigate most appropriate way forward either donate or transfer. | added to agenda | Clerk |  | 2026-10-08
book skip let gilly know | check dates with gilly | Clerk |  | 2026-10-01
look into social value policy | in progress | Clerk |  | 2026-10-08
create laminated sign for the kitchen about not pouring oil down the sinks | in progress | Clerk |  | 2026-10-01
write report for response received from parishioner possible extrordinary meeting | done | Clerk |  | 2026-10-08
order new flag for village hall | done | Clerk |  | 2026-10-01
sort standing orders and financial regs for delegated committee | changed to terms of reference and scheme of delegation | Clerk |  | 2026-10-08
look into tractor run and arrange | speak to rdc | Clerk |  | 2026-10-01
order benches for the playspace and the parry and plaque | In progress | Clerk |  | 2026-10-08
check prices for cllr emails | awaiting quote | Clerk |  | 2026-09-10
order testing kits for water | done | Clerk |  | 2026-09-10
set date for working group for ememergency plan | emailed awaiting reply | Clerk |  | 2026-10-08
Check light in gents toilet | in progress | Clerk |  | 2026-09-10
fill out land registry forms | in progress | Clerk |  | 2026-09-17
quotes for varnish of sign post | done | Clerk |  | 2026-09-10
look into teddy bears picnic event | in progress | Clerk |  | 2026-10-08
sort streetlight | done | Clerk |  | 2026-09-17
create spreadsheet and report for cio email emma about what needs to be included | In progress | Clerk |  | 2026-10-08
set date for apprasials | in progress | Clerk |  | 2026-10-08
Daily/Weekly
Check emails, deal with or answer |  | Clerk/ RFO
Website and Facebook update |  | Clerk/ RFO
Street Light Reports |  | Clerk
Staff support and training |  | RFO
Monthly
Monthly wages |  | RFO
· Basic Tools
· Bank
· Scribe
· Payment list
· Submit to HMRC
Prepare the monthly payment list |  | RFO
Meetings |  | Clerk/ RFO
at least monthly some months more than one meeting
Prepare agenda | 8 Working days before meeting (Monday)
Draft Agenda to Chair & Vice | 8 Working days before meeting (Monday)
Response from Chair & Vice Chair | 6 Working days before meeting (Wednesday)
Issue Papers to councillors | Friday before Meeting
Put Agenda on noticeboards | Friday before Meeting
Put agenda on website & Facebook | Friday before Meeting
Attend Meeting
Write Minutes | Within 5 working days after meeting
Draft Minutes to Chair & Vice | Within 7 working days after meeting
Put on website | Within 10 working days after meeting
Put signed minutes on website | Within 10 working days after meeting | Clerk

## WEBSITE
Action | Comments | Officer | RAG | Raking | Target Date
add wording to minutes page | in progress | Clerk
from september 2025 on add minutes | in progress | Clerk
add pictures to local events page | in progress | Clerk
sort policies page and add new policies to page | in progress | Clerk
find 2023 monthly payments | in progress | Clerk
add 5 years of budget and precept | in progress | Clerk
add audit reports | in progress | Clerk
add more photos to gallery | in progress | Clerk
change sally to emma in contact page | in progress | Clerk
add register of interest to contacts page | in progress | Clerk